## Summary
Validation Report Summary
Updated rule: time mismatches are ignored when Ticket Type = ITD or ITR. Date mismatches are ignored only when Ticket Type = ITD.
Source File | Copy of Field Nation Daily Validation- 04022026.xlsx
Scope | Rows assigned to Field Nation in the Report sheet
Metric | Value
Comparable Tickets | 233
Matched | 185
Errors | 48
Completion % | 79.4
Status Errors | 11
Date Errors | 0
Time Errors (after exceptions) | 25
Name Errors | 13
Date Exceptions Applied | 0
Time Exceptions Applied | 79
ITD Time Exceptions | 78
ITR Time Exceptions | 1

## Validation Details
Validation Details
Core Ticket Data |  |  |  |  | Inside Edge | [5 empty] | Field Nation |  | Validation
Source Row | Acuative Ticket | Ticket Type | Assigned Company | FN Status | IE & FN Status | IE FE Name | FN FE Name | IE Due Date | IE Due Time | IE Scheduled | FN Scheduled Date | FN Scheduled Time | Status Check | Date Check | Time Check | Name Check | Date Exception Applied | Time Exception Applied | Exception Type | Final Result | Issue Details
46 | 3470793 | IIN | Field Nation | Work Done | Error | Abdul Akilo | Abdul Akilo | 2026-04-01 | 08:00 | 2026-04-01 08:00 | 2026-04-01 | 08:00 | Error | OK | OK | OK | No | No | None | Error | IE & FN Status is not OK
47 | 3470843 | ISS | Field Nation | Work Done | Error | Michael Hiter | Michael Hiter | 2026-04-01 | 08:30 | 2026-04-01 08:30 | 2026-04-01 | 08:30 | Error | OK | OK | OK | No | No | None | Error | IE & FN Status is not OK
50 | 3454713 | IIN | Field Nation | Work Done | Error | Daniel Ali | Daniel Ali | 2026-04-01 | 10:00 | 2026-04-01 10:00 | 2026-04-01 | 10:00 | Error | OK | OK | OK | No | No | None | Error | IE & FN Status is not OK
51 | 3470876 | ITR | Field Nation | Work Done | Error | William Ferguson | William Ferguson | 2026-04-01 | 10:30 | 2026-04-01 10:30 | 2026-04-01 | 09:45 | Error | OK | OK | OK | No | Yes | ITR-Time | Error | IE & FN Status is not OK; Time mismatch accepted by ITR exception
52 | 3471336 | IMO | Field Nation | Work Done | Error | Leon Cunningham | Leon Cunningham | 2026-04-01 | 11:00 | 2026-04-01 11:00 | 2026-04-01 | 11:00 | Error | OK | OK | OK | No | No | None | Error | IE & FN Status is not OK
53 | 3471337 | IMO | Field Nation | Work Done | Error | Mark Paulsen | Mark Paulsen | 2026-04-01 | 11:00 | 2026-04-01 11:00 | 2026-04-01 | 11:00 | Error | OK | OK | OK | No | No | None | Error | IE & FN Status is not OK
54 | 3471571 | IMT | Field Nation | Work Done | Error | Ashton Alva | Ashton Alva | 2026-04-01 | 11:00 | 2026-04-01 11:00 | 2026-04-01 | 11:00 | Error | OK | OK | OK | No | No | None | Error | IE & FN Status is not OK
55 | 3470877 | IIN | Field Nation | Work Done | Error | William Ferguson | William Ferguson | 2026-04-01 | 11:00 | 2026-04-01 11:00 | 2026-04-01 | 11:00 | Error | OK | OK | OK | No | No | None | Error | IE & FN Status is not OK
57 | 3441778 | IIN | Field Nation | Assigned | OK | Ozni Benson | Ozni Benson | 2026-04-01 | 11:00 | 2026-04-01 11:00 | 2026-04-01 | 11:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
61 | 3470135 | ICS | Field Nation | Work Done | Error | Juan Clark | Juan Clark | 2026-04-01 | 13:00 | 2026-04-01 13:00 | 2026-04-01 | 13:00 | Error | OK | OK | OK | No | No | None | Error | IE & FN Status is not OK
62 | 3441040 | IIN | Field Nation | Assigned | OK | Chris Esswein | Chris Esswein | 2026-04-01 | 13:00 | 2026-04-01 13:00 | 2026-04-01 | 13:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
70 | 3471667 | IMU | Field Nation | Assigned | OK | Vince Oscar | VINCE OSCAR | 2026-04-01 | 20:00 | 2026-04-01 20:00 | 2026-04-01 | 20:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
71 | 3441779 | ITD | Field Nation | Assigned | OK | Ozni Benson | Ozni Benson | 2026-04-01 | 23:59 | 2026-04-01 20:00 | 2026-04-01 | 11:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
84 | 3441041 | ITD | Field Nation | Assigned | OK | Chris Esswein | Chris Esswein | 2026-04-01 | 23:59 | 2026-04-01 23:59 | 2026-04-01 | 14:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
86 | 3468997 | IIN | Field Nation | Assigned | OK | Daniel Ali | Daniel Ali | 2026-04-02 | 07:30 | 2026-04-02 07:30 | 2026-04-02 | 07:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
87 | 3469001 | IIN | Field Nation | Assigned | OK | Zaeem Shah Gillani | Zaeem shah Gillani | 2026-04-02 | 07:30 | 2026-04-02 07:30 | 2026-04-02 | 07:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
101 | 3433959 | IIN | Field Nation | Assigned | OK | Abiola Makanjuola | Abiola Makanjuola | 2026-04-02 | 08:45 | 2026-04-02 08:45 | 2026-04-02 | 08:45 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
105 | 3471195 | IMT | Field Nation | Assigned | OK | Steven Mccune | Steven McCune | 2026-04-02 | 09:00 | 2026-04-02 09:00 | 2026-04-02 | 09:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
107 | 3471602 | IMS | Field Nation | Assigned | OK | Vince Oscar | VINCE OSCAR | 2026-04-02 | 09:00 | 2026-04-02 09:00 | 2026-04-02 | 09:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
112 | 3465746 | IIN | Field Nation | Assigned | OK | Gary L. Symons | Gary Symons | 2026-04-02 | 09:00 | 2026-04-02 09:00 | 2026-04-02 | 09:00 | OK | OK | OK | Error | No | No | None | Error | IE FE Name ≠ FN FE Name
117 | 3471780 | IMT | Field Nation | Assigned | OK | Kemar Mckenzie | Kemar Mckenzie | 2026-04-02 | 09:00 | 2026-04-02 09:00 | 2026-04-02 | 09:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
123 | 3465883 | ITR | Field Nation | Assigned | OK | Harold Sanders | Harold Sanders | 2026-04-02 | 09:15 | 2026-04-02 09:15 | 2026-04-02 | 09:15 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
128 | 3439436 | IIN | Field Nation | Assigned | OK | Ricky Christopher | Ricky Christopher | 2026-04-02 | 09:30 | 2026-04-02 09:30 | 2026-04-02 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
130 | 3442000 | IIN | Field Nation | Assigned | OK | Ahmed O. Ali | Ahmed Ali | 2026-04-02 | 09:30 | 2026-04-02 09:30 | 2026-04-02 | 09:30 | OK | OK | OK | Error | No | No | None | Error | IE FE Name ≠ FN FE Name
131 | 3446084 | IIN | Field Nation | Assigned | OK | Yvan Dimitri Dzuakou Todem | Yvan Dimitri DZUAKOU TODEM | 2026-04-02 | 09:30 | 2026-04-02 09:30 | 2026-04-02 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
133 | 3465884 | IIN | Field Nation | Assigned | OK | Harold Sanders | Harold Sanders | 2026-04-02 | 09:45 | 2026-04-02 09:45 | 2026-04-02 | 09:45 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
149 | 3471212 | INA | Field Nation | Assigned | OK | Hussein Shalaldah | Hussein Shalaldah | 2026-04-02 | 10:00 | 2026-04-02 10:00 | 2026-04-02 | 10:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
152 | 3440664 | IIN | Field Nation | Assigned | OK | Olivia Wilcroft | Olivia Wilcroft | 2026-04-02 | 10:00 | 2026-04-02 10:00 | 2026-04-02 | 10:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
153 | 3445978 | IIN | Field Nation | Assigned | OK | Harb Salman | Harb Salman | 2026-04-02 | 10:00 | 2026-04-02 10:00 | 2026-04-02 | 10:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
166 | 3471451 | INA | Field Nation | Assigned | OK | Emmanuel Jimenez | Emmanuel Jimenez | 2026-04-02 | 11:00 | 2026-04-02 11:00 | 2026-04-02 | 11:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
171 | 3446261 | IIN | Field Nation | Assigned | OK | Ameh Atokolo | Ameh Atokolo | 2026-04-02 | 11:00 | 2026-04-02 11:00 | 2026-04-02 | 11:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
185 | 3446060 | IIN | Field Nation | Assigned | OK | David Ogunwobi | David Ogunwobi | 2026-04-02 | 12:30 | 2026-04-02 12:30 | 2026-04-02 | 12:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
209 | 3445979 | ITD | Field Nation | Assigned | OK | Harb Salman | Harb Salman | 2026-04-02 | 23:59 | 2026-04-02 15:00 | 2026-04-02 | 13:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
222 | 3440665 | ITD | Field Nation | Assigned | OK | Olivia Wilcroft | Olivia Wilcroft | 2026-04-02 | 23:59 | 2026-04-02 23:00 | 2026-04-02 | 10:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
230 | 3439437 | ITD | Field Nation | Assigned | OK | Ricky Christopher | Ricky Christopher | 2026-04-02 | 23:59 | 2026-04-02 23:59 | 2026-04-02 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
231 | 3442001 | ITD | Field Nation | Assigned | OK | Ahmed O. Ali | Ahmed Ali | 2026-04-02 | 23:59 | 2026-04-02 23:59 | 2026-04-02 | 09:30 | OK | OK | OK | Error | No | Yes | ITD-Time | Error | IE FE Name ≠ FN FE Name; Time mismatch accepted by ITD exception
232 | 3446262 | ITD | Field Nation | Assigned | OK | Ameh Atokolo | Ameh Atokolo | 2026-04-02 | 23:59 | 2026-04-02 23:59 | 2026-04-02 | 11:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
233 | 3446061 | ITD | Field Nation | Assigned | OK | David Ogunwobi | David Ogunwobi | 2026-04-02 | 23:59 | 2026-04-02 23:59 | 2026-04-02 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
234 | 3446085 | ITD | Field Nation | Assigned | OK | Yvan Dimitri Dzuakou Todem | Yvan Dimitri DZUAKOU TODEM | 2026-04-02 | 23:59 | 2026-04-02 23:59 | 2026-04-02 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
251 | 3439975 | IIN | Field Nation | Assigned | OK | Jason Wagster | Jason Wagster | 2026-04-03 | 09:30 | 2026-04-03 09:30 | 2026-04-03 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
255 | 3446082 | IIN | Field Nation | Assigned | OK | Neuer Alsibai | Neuer Alsibai | 2026-04-03 | 09:30 | 2026-04-03 09:30 | 2026-04-03 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
257 | 3432765 | IIN | Field Nation | Assigned | OK | Yash Patel | Yash Patel | 2026-04-03 | 09:45 | 2026-04-03 09:45 | 2026-04-03 | 09:45 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
258 | 3452947 | IIN | Field Nation | Assigned | OK | Ivan Gonzalez | Ivan Gonzalez | 2026-04-03 | 09:45 | 2026-04-03 09:45 | 2026-04-03 | 09:45 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
262 | 3431588 | IIN | Field Nation | Assigned | OK | Alexander Mordi | Alexander Mordi | 2026-04-03 | 10:00 | 2026-04-03 10:00 | 2026-04-03 | 10:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
309 | 3439976 | ITD | Field Nation | Assigned | OK | Jason Wagster | Jason Wagster | 2026-04-03 | 23:59 | 2026-04-03 23:59 | 2026-04-03 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
310 | 3446083 | ITD | Field Nation | Assigned | OK | Neuer Alsibai | Neuer Alsibai | 2026-04-03 | 23:59 | 2026-04-03 23:59 | 2026-04-03 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
312 | 3471790 | IMO | Field Nation | Assigned | OK | Prince Obidike | Prince Obidike | 2026-04-04 | 03:00 | 2026-04-04 03:00 | 2026-04-04 | 03:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
320 | 3471090 | IIN | Field Nation | Assigned | OK | Olalekan Phillips | Olalekan Phillips | 2026-04-06 | 06:00 | 2026-04-06 06:00 | 2026-04-06 | 06:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
339 | 3470616 | IIN | Field Nation | Assigned | OK | Alex Villarreal | Alex Villarreal | 2026-04-06 | 09:00 | 2026-04-06 09:00 | 2026-04-06 | 09:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
369 | 3446014 | IIN | Field Nation | Assigned | OK | Sai Prakash Reddy Atluri | Sai Prakash Reddy Atluri | 2026-04-06 | 10:30 | 2026-04-06 10:30 | 2026-04-06 | 10:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
402 | 3446015 | ITD | Field Nation | Assigned | OK | Sai Prakash Reddy Atluri | Sai Prakash Reddy Atluri | 2026-04-06 | 23:59 | 2026-04-06 20:00 | 2026-04-06 | 10:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
413 | 3469017 | IIN | Field Nation | Assigned | OK | Alfred Farrow | Alfred Farrow | 2026-04-07 | 07:30 | 2026-04-07 07:30 | 2026-04-07 | 07:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
429 | 3471280 | INA | Field Nation | Assigned | OK | Eduardo J. Saucedo | Eduardo Saucedo | 2026-04-07 | 09:00 | 2026-04-07 09:00 | 2026-04-07 | 09:00 | OK | OK | OK | Error | No | No | None | Error | IE FE Name ≠ FN FE Name
448 | 3439927 | IIN | Field Nation | Assigned | OK | Harpreet Singh | Harpreet Singh | 2026-04-07 | 10:00 | 2026-04-07 10:00 | 2026-04-07 | 10:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
450 | 3445962 | IIN | Field Nation | Assigned | OK | Kabir Kareem | KABIR KAREEM | 2026-04-07 | 10:30 | 2026-04-07 10:30 | 2026-04-07 | 10:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
453 | 3440964 | IIN | Field Nation | Assigned | OK | Amin Sanchez | Amin Sanchez | 2026-04-07 | 11:00 | 2026-04-07 11:00 | 2026-04-07 | 11:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
461 | 3446030 | IIN | Field Nation | Assigned | OK | Adewale Adesona | Adewale Adesona | 2026-04-07 | 12:00 | 2026-04-07 12:00 | 2026-04-07 | 12:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
479 | 3440965 | ITD | Field Nation | Assigned | OK | Amin Sanchez | Amin Sanchez | 2026-04-07 | 23:59 | 2026-04-07 20:00 | 2026-04-07 | 11:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
481 | 3439928 | ITD | Field Nation | Assigned | OK | Harpreet Singh | Harpreet Singh | 2026-04-07 | 23:59 | 2026-04-07 23:59 | 2026-04-07 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
482 | 3445963 | ITD | Field Nation | Assigned | OK | Kabir Kareem | KABIR KAREEM | 2026-04-07 | 23:59 | 2026-04-07 23:59 | 2026-04-07 | 06:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
483 | 3446031 | ITD | Field Nation | Assigned | OK | Adewale Adesona | Adewale Adesona | 2026-04-07 | 23:59 | 2026-04-07 23:59 | 2026-04-07 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
514 | 3445944 | IIN | Field Nation | Assigned | OK | Suresh Venkatachalam | Suresh Venkatachalam | 2026-04-08 | 09:30 | 2026-04-08 09:30 | 2026-04-08 | 03:30 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
515 | 3441494 | IIN | Field Nation | Assigned | OK | Daniel Ali | Daniel Ali | 2026-04-08 | 09:30 | 2026-04-08 09:30 | 2026-04-08 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
516 | 3440083 | IIN | Field Nation | Assigned | OK | Jerome Chambers | Jerome Chambers | 2026-04-08 | 09:30 | 2026-04-08 09:30 | 2026-04-08 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
525 | 3441536 | IIN | Field Nation | Assigned | OK | Ricki Cole | Ricki Cole | 2026-04-08 | 10:00 | 2026-04-08 10:00 | 2026-04-08 | 10:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
530 | 3445984 | IIN | Field Nation | Assigned | OK | Oladapo Oliyide | OLADAPO OLIYIDE | 2026-04-08 | 11:00 | 2026-04-08 11:00 | 2026-04-08 | 11:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
546 | 3446066 | IIN | Field Nation | Assigned | OK | Nnamdi Igbokwe | Nnamdi Igbokwe | 2026-04-08 | 13:00 | 2026-04-08 13:00 | 2026-04-08 | 13:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
556 | 3441495 | ITD | Field Nation | Assigned | OK | Daniel Ali | Daniel Ali | 2026-04-08 | 23:59 | 2026-04-08 20:00 | 2026-04-08 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
557 | 3441537 | ITD | Field Nation | Assigned | OK | Ricki Cole | Ricki Cole | 2026-04-08 | 23:59 | 2026-04-08 20:00 | 2026-04-08 | 10:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
558 | 3440084 | ITD | Field Nation | Assigned | OK | Jerome Chambers | Jerome Chambers | 2026-04-08 | 23:59 | 2026-04-08 20:00 | 2026-04-08 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
562 | 3445945 | ITD | Field Nation | Assigned | OK | Suresh Venkatachalam | Suresh Venkatachalam | 2026-04-08 | 23:59 | 2026-04-08 23:59 | 2026-04-08 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
563 | 3445985 | ITD | Field Nation | Assigned | OK | Oladapo Oliyide | OLADAPO OLIYIDE | 2026-04-08 | 23:59 | 2026-04-08 23:59 | 2026-04-08 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
564 | 3446067 | ITD | Field Nation | Assigned | OK | Nnamdi Igbokwe | Nnamdi Igbokwe | 2026-04-08 | 23:59 | 2026-04-08 23:59 | 2026-04-08 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
570 | 3469057 | IIN | Field Nation | Assigned | OK | Cesar Vidal | Cesar Vidal | 2026-04-09 | 07:30 | 2026-04-09 07:30 | 2026-04-09 | 07:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
571 | 3469061 | IIN | Field Nation | Assigned | OK | Chigozie Ogbuji | CHIGOZIE OGBUJI | 2026-04-09 | 07:30 | 2026-04-09 07:30 | 2026-04-09 | 07:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
586 | 3441306 | IIN | Field Nation | Assigned | OK | Jason Wagster | Jason Wagster | 2026-04-09 | 09:30 | 2026-04-09 09:30 | 2026-04-09 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
608 | 3441434 | IIN | Field Nation | Assigned | OK | Tom Perachio | Tom Perachio | 2026-04-09 | 11:30 | 2026-04-09 11:30 | 2026-04-09 | 11:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
611 | 3440059 | IIN | Field Nation | Assigned | OK | Jonathan Taufer | Jonathan Taufer | 2026-04-09 | 12:00 | 2026-04-09 12:00 | 2026-04-09 | 12:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
632 | 3441435 | ITD | Field Nation | Assigned | OK | Tom Perachio | Tom Perachio | 2026-04-09 | 23:59 | 2026-04-09 20:00 | 2026-04-09 | 11:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
633 | 3440060 | ITD | Field Nation | Assigned | OK | Jonathan Taufer | Jonathan Taufer | 2026-04-09 | 23:59 | 2026-04-09 20:00 | 2026-04-09 | 12:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
639 | 3441307 | ITD | Field Nation | Assigned | OK | Jason Wagster | Jason Wagster | 2026-04-09 | 23:59 | 2026-04-09 23:59 | 2026-04-09 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
643 | 3446027 | ITD | Field Nation | Assigned | OK | Gagandeep Singh | Gagandeep Singh | 2026-04-10 | 23:59 | 2026-04-10 08:00 | 2026-04-10 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
653 | 3441456 | IIN | Field Nation | Assigned | OK | Lydell Emerson | Lydell Emerson | 2026-04-10 | 09:30 | 2026-04-10 09:30 | 2026-04-10 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
654 | 3446026 | IIN | Field Nation | Assigned | OK | Gagandeep Singh | Gagandeep Singh | 2026-04-10 | 09:30 | 2026-04-10 09:30 | 2026-04-10 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
674 | 3440191 | IIN | Field Nation | Assigned | OK | Johnnie Mcleod | Johnnie McLeod | 2026-04-10 | 12:00 | 2026-04-10 12:00 | 2026-04-10 | 12:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
676 | 3445974 | IIN | Field Nation | Assigned | OK | Kail Vigneswaran | Kail Vigneswaran | 2026-04-10 | 12:00 | 2026-04-10 12:00 | 2026-04-10 | 12:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
694 | 3441457 | ITD | Field Nation | Assigned | OK | Lydell Emerson | Lydell Emerson | 2026-04-10 | 23:59 | 2026-04-10 23:59 | 2026-04-10 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
695 | 3440192 | ITD | Field Nation | Assigned | OK | Johnnie Mcleod | Johnnie McLeod | 2026-04-10 | 23:59 | 2026-04-10 23:59 | 2026-04-10 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
696 | 3445975 | ITD | Field Nation | Assigned | OK | Kail Vigneswaran | Kail Vigneswaran | 2026-04-10 | 23:59 | 2026-04-10 23:59 | 2026-04-10 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
708 | 3458530 | IIN | Field Nation | Assigned | OK | Stefalonicus A. Marcius | Stephanicus Marcyus | 2026-04-13 | 05:00 | 2026-04-13 05:00 | 2026-04-13 | 05:00 | OK | OK | OK | Error | No | No | None | Error | IE FE Name ≠ FN FE Name
709 | 3458695 | IIN | Field Nation | Assigned | OK | Dell Collier | Dell Collier | 2026-04-13 | 05:30 | 2026-04-13 05:30 | 2026-04-13 | 05:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
710 | 3471093 | IIN | Field Nation | Assigned | OK | Taofeek Fasugba | Taofeek Fasugba | 2026-04-13 | 06:00 | 2026-04-13 06:00 | 2026-04-13 | 06:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
738 | 3441102 | IIN | Field Nation | Assigned | OK | Ademola Kuku | Ademola Kuku | 2026-04-13 | 11:00 | 2026-04-13 11:00 | 2026-04-13 | 11:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
745 | 3446028 | IIN | Field Nation | Assigned | OK | Oladapo Oliyide | OLADAPO OLIYIDE | 2026-04-13 | 11:30 | 2026-04-13 11:30 | 2026-04-13 | 11:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
765 | 3441103 | ITD | Field Nation | Assigned | OK | Ademola Kuku | Ademola Kuku | 2026-04-13 | 23:59 | 2026-04-13 20:00 | 2026-04-13 | 11:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
768 | 3446029 | ITD | Field Nation | Assigned | OK | Oladapo Oliyide | OLADAPO OLIYIDE | 2026-04-13 | 23:59 | 2026-04-13 23:59 | 2026-04-13 | 13:45 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
770 | 3469073 | IIN | Field Nation | Assigned | OK | Steve Maher | Steve Maher | 2026-04-14 | 07:30 | 2026-04-14 07:30 | 2026-04-14 | 07:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
780 | 3471129 | IIN | Field Nation | Assigned | OK | Jefferson Therlonge | Jefferson Therlonge | 2026-04-14 | 09:00 | 2026-04-14 09:00 | 2026-04-14 | 09:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
788 | 3440212 | IIN | Field Nation | Assigned | OK | Daniel Jordan | Daniel Jordan | 2026-04-14 | 09:30 | 2026-04-14 09:30 | 2026-04-14 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
807 | 3441146 | IIN | Field Nation | Assigned | OK | Joshua Evans | Joshua Evans | 2026-04-14 | 11:00 | 2026-04-14 11:00 | 2026-04-14 | 11:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
808 | 3445998 | IIN | Field Nation | Assigned | OK | Dawit Telahun | Dawit Telahun | 2026-04-14 | 11:00 | 2026-04-14 11:00 | 2026-04-14 | 11:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
823 | 3441150 | IIN | Field Nation | Assigned | OK | Mario Boatwright | Mario Boatwright | 2026-04-14 | 13:00 | 2026-04-14 13:00 | 2026-04-14 | 13:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
836 | 3441147 | ITD | Field Nation | Assigned | OK | Joshua Evans | Joshua Evans | 2026-04-14 | 23:59 | 2026-04-14 23:59 | 2026-04-14 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
837 | 3441151 | ITD | Field Nation | Assigned | OK | Mario Boatwright | Mario Boatwright | 2026-04-14 | 23:59 | 2026-04-14 23:59 | 2026-04-14 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
838 | 3440213 | ITD | Field Nation | Assigned | OK | Daniel Jordan | Daniel Jordan | 2026-04-14 | 23:59 | 2026-04-14 23:59 | 2026-04-14 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
839 | 3445999 | ITD | Field Nation | Assigned | OK | Dawit Telahun | Dawit Telahun | 2026-04-14 | 23:59 | 2026-04-14 23:59 | 2026-04-14 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
844 | 3469096 | IIN | Field Nation | Assigned | OK | Steven Glus | Steven Glus | 2026-04-15 | 07:00 | 2026-04-15 07:00 | 2026-04-15 | 07:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
875 | 3437353 | IIN | Field Nation | Assigned | OK | Ndifreke Asuquo | Ndifreke Asuquo | 2026-04-15 | 12:00 | 2026-04-15 12:00 | 2026-04-15 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
878 | 3441376 | IIN | Field Nation | Assigned | OK | Frank Shoffner | FRANK SHOFFNER | 2026-04-15 | 12:00 | 2026-04-15 12:00 | 2026-04-15 | 12:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
880 | 3446000 | IIN | Field Nation | Assigned | OK | David Edojah | David Edojah | 2026-04-15 | 12:00 | 2026-04-15 12:00 | 2026-04-15 | 12:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
882 | 3446090 | IIN | Field Nation | Assigned | OK | Abdurzag Abdunur | Abdurzag Abdunur | 2026-04-15 | 12:00 | 2026-04-15 12:00 | 2026-04-15 | 12:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
899 | 3441377 | ITD | Field Nation | Assigned | OK | Frank Shoffner | FRANK SHOFFNER | 2026-04-15 | 23:59 | 2026-04-15 23:59 | 2026-04-15 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
900 | 3446001 | ITD | Field Nation | Assigned | OK | David Edojah | David Edojah | 2026-04-15 | 23:59 | 2026-04-15 23:59 | 2026-04-15 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
901 | 3446091 | ITD | Field Nation | Assigned | OK | Abdurzag Abdunur | Abdurzag Abdunur | 2026-04-15 | 23:59 | 2026-04-15 23:59 | 2026-04-15 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
923 | 3445966 | IIN | Field Nation | Assigned | OK | Gull Hassan | Gull Hassan | 2026-04-16 | 09:30 | 2026-04-16 09:30 | 2026-04-16 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
935 | 3441056 | IIN | Field Nation | Assigned | OK | Overton Kelly | Overton Kelly | 2026-04-16 | 11:00 | 2026-04-16 11:00 | 2026-04-16 | 11:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
936 | 3446034 | IIN | Field Nation | Assigned | OK | Gagandeep Singh | Gagandeep Singh | 2026-04-16 | 11:00 | 2026-04-16 11:00 | 2026-04-16 | 11:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
941 | 3441078 | IIN | Field Nation | Assigned | OK | Dwiuan White | Dwiuan White | 2026-04-16 | 12:00 | 2026-04-16 12:00 | 2026-04-16 | 12:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
959 | 3441057 | ITD | Field Nation | Assigned | OK | Overton Kelly | Overton Kelly | 2026-04-16 | 23:59 | 2026-04-16 23:00 | 2026-04-16 | 11:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
965 | 3441079 | ITD | Field Nation | Assigned | OK | Dwiuan White | Dwiuan White | 2026-04-16 | 23:59 | 2026-04-16 23:59 | 2026-04-16 | 12:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
966 | 3445967 | ITD | Field Nation | Assigned | OK | Gull Hassan | Gull Hassan | 2026-04-16 | 23:59 | 2026-04-16 23:59 | 2026-04-16 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
967 | 3446035 | ITD | Field Nation | Assigned | OK | Gagandeep Singh | Gagandeep Singh | 2026-04-16 | 23:59 | 2026-04-16 23:59 | 2026-04-16 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
975 | 3439463 | IIN | Field Nation | Assigned | OK | Jamiel Shelton | Jamiel Shelton | 2026-04-17 | 09:30 | 2026-04-17 09:30 | 2026-04-17 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
981 | 3446267 | IIN | Field Nation | Assigned | OK | Josh Daynes | Josh Daynes | 2026-04-17 | 10:30 | 2026-04-17 10:30 | 2026-04-17 | 10:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
984 | 3441198 | IIN | Field Nation | Assigned | OK | Stephen Antwi | Stephen Antwi | 2026-04-17 | 11:30 | 2026-04-17 11:30 | 2026-04-17 | 11:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
995 | 3441200 | IIN | Field Nation | Assigned | OK | Jamiel Shelton | Jamiel Shelton | 2026-04-17 | 13:00 | 2026-04-17 13:00 | 2026-04-17 | 13:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1002 | 3439464 | ITD | Field Nation | Assigned | OK | Jamiel Shelton | Jamiel Shelton | 2026-04-17 | 23:59 | 2026-04-17 17:00 | 2026-04-17 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1003 | 3441199 | ITD | Field Nation | Assigned | OK | Stephen Antwi | Stephen Antwi | 2026-04-17 | 23:59 | 2026-04-17 23:59 | 2026-04-17 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1004 | 3441201 | ITD | Field Nation | Assigned | OK | Jamiel Shelton | Jamiel Shelton | 2026-04-17 | 23:59 | 2026-04-17 23:59 | 2026-04-17 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1005 | 3446268 | ITD | Field Nation | Assigned | OK | Josh Daynes | Josh Daynes | 2026-04-17 | 23:59 | 2026-04-17 23:59 | 2026-04-17 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1017 | 3446223 | IIN | Field Nation | Assigned | OK | Kabir Kareem | KABIR KAREEM | 2026-04-20 | 09:30 | 2026-04-20 09:30 | 2026-04-20 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1018 | 3445970 | IIN | Field Nation | Assigned | OK | Victor Isac | Victor Isac | 2026-04-20 | 09:30 | 2026-04-20 09:30 | 2026-04-20 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1022 | 3441730 | IIN | Field Nation | Assigned | OK | Derek Francis Domingo | Derek Francis Domingo | 2026-04-20 | 10:00 | 2026-04-20 10:00 | 2026-04-20 | 10:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1049 | 3441731 | ITD | Field Nation | Assigned | OK | Derek Francis Domingo | Derek Francis Domingo | 2026-04-20 | 23:59 | 2026-04-20 17:00 | 2026-04-20 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1051 | 3446224 | ITD | Field Nation | Assigned | OK | Kabir Kareem | KABIR KAREEM | 2026-04-20 | 23:59 | 2026-04-20 23:59 | 2026-04-20 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1052 | 3445971 | ITD | Field Nation | Assigned | OK | Victor Isac | Victor Isac | 2026-04-20 | 23:59 | 2026-04-20 23:59 | 2026-04-20 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1069 | 3445972 | IIN | Field Nation | Assigned | OK | Oladapo Oliyide | OLADAPO OLIYIDE | 2026-04-21 | 09:30 | 2026-04-21 09:30 | 2026-04-21 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1070 | 3446002 | IIN | Field Nation | Assigned | OK | Kabir Kareem | KABIR KAREEM | 2026-04-21 | 09:30 | 2026-04-21 09:30 | 2026-04-21 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1078 | 3446111 | IIN | Field Nation | Assigned | OK | Chris Born | Chris Born | 2026-04-21 | 10:30 | 2026-04-21 10:30 | 2026-04-21 | 10:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1083 | 3441662 | IIN | Field Nation | Assigned | OK | Mor Ndiaye | Mor Ndiaye | 2026-04-21 | 11:00 | 2026-04-21 11:00 | 2026-04-21 | 11:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1097 | 3441332 | IIN | Field Nation | Assigned | OK | Daniel Jordan | Daniel Jordan | 2026-04-21 | 13:00 | 2026-04-21 13:00 | 2026-04-21 | 13:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1101 | 3470005 | IIN | Field Nation | Assigned | OK | Danish Mahmood | Danish Mahmood | 2026-04-21 | 16:00 | 2026-04-21 16:00 | 2026-04-21 | 16:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1103 | 3441333 | ITD | Field Nation | Assigned | OK | Daniel Jordan | Daniel Jordan | 2026-04-21 | 23:59 | 2026-04-21 23:59 | 2026-04-21 | 03:15 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1104 | 3441663 | ITD | Field Nation | Assigned | OK | Mor Ndiaye | Mor Ndiaye | 2026-04-21 | 23:59 | 2026-04-21 23:59 | 2026-04-21 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1105 | 3445973 | ITD | Field Nation | Assigned | OK | Oladapo Oliyide | OLADAPO OLIYIDE | 2026-04-21 | 23:59 | 2026-04-21 23:59 | 2026-04-21 | 12:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1106 | 3446003 | ITD | Field Nation | Assigned | OK | Kabir Kareem | KABIR KAREEM | 2026-04-21 | 23:59 | 2026-04-21 23:59 | 2026-04-21 | 12:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1107 | 3446112 | ITD | Field Nation | Assigned | OK | Chris Born | Chris Born | 2026-04-21 | 23:59 | 2026-04-21 23:59 | 2026-04-21 | 12:45 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1111 | 3469144 | IIN | Field Nation | Assigned | OK | Gabriel Phelan | Gabriel Phelan | 2026-04-22 | 07:00 | 2026-04-22 07:00 | 2026-04-22 | 07:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1130 | 3446104 | IIN | Field Nation | Assigned | OK | Oladapo Oliyide | OLADAPO OLIYIDE | 2026-04-22 | 09:30 | 2026-04-22 09:30 | 2026-04-22 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1136 | 3445990 | IIN | Field Nation | Assigned | OK | Kabir Kareem | KABIR KAREEM | 2026-04-22 | 10:30 | 2026-04-22 10:30 | 2026-04-22 | 10:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1158 | 3445991 | ITD | Field Nation | Assigned | OK | Kabir Kareem | KABIR KAREEM | 2026-04-22 | 23:59 | 2026-04-22 23:59 | 2026-04-22 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1159 | 3446105 | ITD | Field Nation | Assigned | OK | Oladapo Oliyide | OLADAPO OLIYIDE | 2026-04-22 | 23:59 | 2026-04-22 23:59 | 2026-04-22 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1163 | 3469160 | IIN | Field Nation | Assigned | OK | Igor Gorosciuc | Igor Gorosciuc | 2026-04-23 | 07:00 | 2026-04-23 07:00 | 2026-04-23 | 07:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1173 | 3439616 | IIN | Field Nation | Assigned | OK | Erin Scofield | Erin Scofield | 2026-04-23 | 09:30 | 2026-04-23 09:30 | 2026-04-23 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1174 | 3446225 | IIN | Field Nation | Assigned | OK | Oladapo Oliyide | OLADAPO OLIYIDE | 2026-04-23 | 09:30 | 2026-04-23 09:30 | 2026-04-23 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1175 | 3445996 | IIN | Field Nation | Assigned | OK | Shumail Feroz | Shumail Feroz | 2026-04-23 | 09:30 | 2026-04-23 09:30 | 2026-04-23 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1181 | 3445994 | IIN | Field Nation | Assigned | OK | Dawit Telahun | Dawit Telahun | 2026-04-23 | 10:30 | 2026-04-23 10:30 | 2026-04-23 | 10:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1182 | 3446070 | IIN | Field Nation | Assigned | OK | Todd John Soukoreff | Chris Born | 2026-04-23 | 10:30 | 2026-04-23 10:30 | 2026-04-23 | 10:30 | OK | OK | OK | Error | No | No | None | Error | IE FE Name ≠ FN FE Name
1197 | 3439617 | ITD | Field Nation | Assigned | OK | Erin Scofield | Erin Scofield | 2026-04-23 | 23:59 | 2026-04-23 20:00 | 2026-04-23 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1201 | 3446226 | ITD | Field Nation | Assigned | OK | Oladapo Oliyide | OLADAPO OLIYIDE | 2026-04-23 | 23:59 | 2026-04-23 23:59 | 2026-04-23 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1202 | 3445995 | ITD | Field Nation | Assigned | OK | Dawit Telahun | Dawit Telahun | 2026-04-23 | 23:59 | 2026-04-23 23:59 | 2026-04-23 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1203 | 3445997 | ITD | Field Nation | Assigned | OK | Shumail Feroz | Shumail Feroz | 2026-04-23 | 23:59 | 2026-04-23 23:59 | 2026-04-23 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1204 | 3446071 | ITD | Field Nation | Assigned | OK | Todd John Soukoreff | Chris Born | 2026-04-23 | 23:59 | 2026-04-23 23:59 | 2026-04-23 | 08:00 | OK | OK | OK | Error | No | Yes | ITD-Time | Error | IE FE Name ≠ FN FE Name; Time mismatch accepted by ITD exception
1214 | 3446227 | IIN | Field Nation | Assigned | OK | Kabir Kareem | KABIR KAREEM | 2026-04-24 | 09:30 | 2026-04-24 09:30 | 2026-04-24 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1219 | 3446078 | IIN | Field Nation | Assigned | OK | Renat Galiev | Renat Galiev | 2026-04-24 | 10:15 | 2026-04-24 10:15 | 2026-04-24 | 10:15 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1242 | 3446228 | ITD | Field Nation | Assigned | OK | Kabir Kareem | KABIR KAREEM | 2026-04-24 | 23:59 | 2026-04-24 23:59 | 2026-04-24 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1243 | 3446079 | ITD | Field Nation | Assigned | OK | Renat Galiev | Renat Galiev | 2026-04-24 | 23:59 | 2026-04-24 23:59 | 2026-04-24 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1246 | 3468199 | IIN | Field Nation | Assigned | OK | Gary L. Symons | Gary Symons | 2026-04-27 | 09:00 | 2026-04-27 09:00 | 2026-04-27 | 09:00 | OK | OK | OK | Error | No | No | None | Error | IE FE Name ≠ FN FE Name
1251 | 3441446 | IIN | Field Nation | Assigned | OK | Ashley Mattera | Ashley Mattera | 2026-04-27 | 09:30 | 2026-04-27 09:30 | 2026-04-27 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1266 | 3439610 | IIN | Field Nation | Assigned | OK | Joshua Evans | Joshua Evans | 2026-04-27 | 12:00 | 2026-04-27 12:00 | 2026-04-27 | 12:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1267 | 3445964 | IIN | Field Nation | Assigned | OK | Kabir Kareem | KABIR KAREEM | 2026-04-27 | 12:00 | 2026-04-27 12:00 | 2026-04-27 | 12:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1280 | 3441447 | ITD | Field Nation | Assigned | OK | Ashley Mattera | Ashley Mattera | 2026-04-27 | 23:59 | 2026-04-27 23:59 | 2026-04-27 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1281 | 3439611 | ITD | Field Nation | Assigned | OK | Joshua Evans | Joshua Evans | 2026-04-27 | 23:59 | 2026-04-27 23:59 | 2026-04-27 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1282 | 3445965 | ITD | Field Nation | Assigned | OK | Kabir Kareem | KABIR KAREEM | 2026-04-27 | 23:59 | 2026-04-27 23:59 | 2026-04-27 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1283 | 3469168 | IIN | Field Nation | Assigned | OK | Alfred Farrow | Alfred Farrow | 2026-04-28 | 07:00 | 2026-04-28 07:00 | 2026-04-28 | 07:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1284 | 3469172 | IIN | Field Nation | Assigned | OK |  | Faisal Suleman | 2026-04-28 | 07:00 | 2026-04-28 07:00 | 2026-04-28 | 07:00 | OK | OK | OK | Error | No | No | None | Error | IE FE Name ≠ FN FE Name
1285 | 3469176 | IIN | Field Nation | Assigned | OK |  | OLADAPO OLIYIDE | 2026-04-28 | 07:00 | 2026-04-28 07:00 | 2026-04-28 | 07:00 | OK | OK | OK | Error | No | No | None | Error | IE FE Name ≠ FN FE Name
1290 | 3470631 | IIN | Field Nation | Assigned | OK | Mitchell Treagan | Mitchell Treagan | 2026-04-28 | 09:00 | 2026-04-28 09:00 | 2026-04-28 | 09:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1309 | 3446237 | IIN | Field Nation | Assigned | OK | Asad Khalid Ansari | Asad Khalid Ansari | 2026-04-28 | 11:30 | 2026-04-28 11:30 | 2026-04-28 | 11:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1326 | 3446238 | ITD | Field Nation | Assigned | OK | Asad Khalid Ansari | Asad Khalid Ansari | 2026-04-28 | 23:59 | 2026-04-28 23:59 | 2026-04-28 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1350 | 3441510 | IIN | Field Nation | Assigned | OK | Ned Gill | Ned Gill | 2026-04-29 | 11:00 | 2026-04-29 11:00 | 2026-04-29 | 11:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1371 | 3441511 | ITD | Field Nation | Assigned | OK | Ned Gill | Ned Gill | 2026-04-29 | 23:59 | 2026-04-29 20:00 | 2026-04-29 | 11:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1382 | 3440530 | IIN | Field Nation | Assigned | OK | Oladipupo Ogungbile | Oladipupo Ogungbile | 2026-04-30 | 09:30 | 2026-04-30 09:30 | 2026-04-30 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1387 | 3446008 | IIN | Field Nation | Assigned | OK | Rupinderjit Singh Malhi | Rupinderjit Singh Malhi | 2026-04-30 | 10:30 | 2026-04-30 10:30 | 2026-04-30 | 10:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1394 | 3439445 | IIN | Field Nation | Assigned | OK | Daniel L. Durham | Daniel Durham | 2026-04-30 | 13:00 | 2026-04-30 13:00 | 2026-04-30 | 13:00 | OK | OK | OK | Error | No | No | None | Error | IE FE Name ≠ FN FE Name
1410 | 3439446 | ITD | Field Nation | Assigned | OK | Daniel L. Durham | Daniel Durham | 2026-04-30 | 23:59 | 2026-04-30 23:59 | 2026-04-30 | 15:00 | OK | OK | OK | Error | No | Yes | ITD-Time | Error | IE FE Name ≠ FN FE Name; Time mismatch accepted by ITD exception
1411 | 3440531 | ITD | Field Nation | Assigned | OK | Oladipupo Ogungbile | Oladipupo Ogungbile | 2026-04-30 | 23:59 | 2026-04-30 23:59 | 2026-04-30 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1412 | 3446009 | ITD | Field Nation | Assigned | OK | Rupinderjit Singh Malhi | Rupinderjit Singh Malhi | 2026-04-30 | 23:59 | 2026-04-30 23:59 | 2026-04-30 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1420 | 3446020 | IIN | Field Nation | Assigned | OK | Richard Dey | Richard Dey | 2026-05-01 | 09:30 | 2026-05-01 09:30 | 2026-05-01 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1423 | 3446253 | IIN | Field Nation | Assigned | OK | Chris Born | Chris Born | 2026-05-01 | 10:30 | 2026-05-01 10:30 | 2026-05-01 | 10:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1427 | 3441004 | IIN | Field Nation | Assigned | OK | Anthony Clark | Anthony Clark | 2026-05-01 | 12:00 | 2026-05-01 12:00 | 2026-05-01 | 12:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1445 | 3441005 | ITD | Field Nation | Assigned | OK | Anthony Clark | Anthony Clark | 2026-05-01 | 23:59 | 2026-05-01 17:00 | 2026-05-01 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1447 | 3446021 | ITD | Field Nation | Assigned | OK | Richard Dey | Richard Dey | 2026-05-01 | 23:59 | 2026-05-01 23:59 | 2026-05-01 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1448 | 3446254 | ITD | Field Nation | Assigned | OK | Chris Born | Chris Born | 2026-05-01 | 23:59 | 2026-05-01 23:59 | 2026-05-01 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1455 | 3471435 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-05-04 | 23:59 | 2026-05-04 10:00 | 2026-05-04 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1491 | 3471436 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-05-05 | 23:59 | 2026-05-05 10:00 | 2026-05-05 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1522 | 3471438 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-05-06 | 23:59 | 2026-05-06 10:00 | 2026-05-06 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1525 | 3440077 | IIN | Field Nation | Assigned | OK | Zachary Jones | Zachary Jones | 2026-05-06 | 12:00 | 2026-05-06 12:00 | 2026-05-06 | 12:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1526 | 3440236 | IIN | Field Nation | Assigned | OK | Brian Kloss | Brian Kloss | 2026-05-06 | 12:00 | 2026-05-06 12:00 | 2026-05-06 | 12:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1533 | 3440078 | ITD | Field Nation | Assigned | OK | Zachary Jones | Zachary Jones | 2026-05-06 | 23:59 | 2026-05-06 23:59 | 2026-05-06 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1534 | 3440237 | ITD | Field Nation | Assigned | OK | Brian Kloss | Brian Kloss | 2026-05-06 | 23:59 | 2026-05-06 23:59 | 2026-05-06 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1535 | 3469268 | IIN | Field Nation | Assigned | OK | Alfred Farrow | Alfred Farrow | 2026-05-07 | 07:00 | 2026-05-07 07:00 | 2026-05-07 | 07:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1539 | 3469264 | IIN | Field Nation | Assigned | OK | Basit Olayiwola | Basit Olayiwola | 2026-05-07 | 08:00 | 2026-05-07 08:00 | 2026-05-07 | 08:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1541 | 3471439 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-05-07 | 23:59 | 2026-05-07 10:00 | 2026-05-07 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1545 | 3456104 | INA | Field Nation | Assigned | OK | Patrick Forrester | Patrick Forrester | 2026-05-11 | 10:00 | 2026-05-11 10:00 | 2026-05-11 | 10:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1547 | 3456106 | INA | Field Nation | Assigned | OK | Patrick Forrester | Patrick Forrester | 2026-05-12 | 10:00 | 2026-05-12 10:00 | 2026-05-12 | 10:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
1568 | 3470903 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-08 | 23:59 | 2026-06-08 10:00 | 2026-06-08 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1569 | 3470904 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-09 | 23:59 | 2026-06-09 10:00 | 2026-06-09 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1571 | 3470905 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-10 | 23:59 | 2026-06-10 10:00 | 2026-06-10 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1574 | 3470906 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-11 | 23:59 | 2026-06-11 10:00 | 2026-06-11 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1577 | 3470908 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-12 | 23:59 | 2026-06-12 10:00 | 2026-06-12 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1580 | 3470909 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-13 | 23:59 | 2026-06-13 10:00 | 2026-06-13 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1583 | 3470910 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-14 | 23:59 | 2026-06-14 10:00 | 2026-06-14 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1586 | 3470911 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-15 | 23:59 | 2026-06-15 10:00 | 2026-06-15 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1589 | 3470912 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-16 | 23:59 | 2026-06-16 10:00 | 2026-06-16 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1592 | 3470913 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-17 | 23:59 | 2026-06-17 10:00 | 2026-06-17 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1596 | 3470914 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-18 | 23:59 | 2026-06-18 10:00 | 2026-06-18 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1599 | 3470915 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-19 | 23:59 | 2026-06-19 10:00 | 2026-06-19 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1602 | 3470916 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-20 | 23:59 | 2026-06-20 10:00 | 2026-06-20 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1605 | 3470917 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-21 | 23:59 | 2026-06-21 10:00 | 2026-06-21 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1608 | 3470919 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-22 | 23:59 | 2026-06-22 10:00 | 2026-06-22 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1609 | 3470922 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-23 | 23:59 | 2026-06-23 10:00 | 2026-06-23 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1610 | 3470923 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-24 | 23:59 | 2026-06-24 10:00 | 2026-06-24 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1611 | 3470924 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-25 | 23:59 | 2026-06-25 10:00 | 2026-06-25 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1612 | 3419497 | IIN | Field Nation | Assigned | OK | Adeola Ajayi | Adeola Ajayi | 2026-08-19 | 12:00 | 2026-08-19 12:00 | 2026-08-19 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
2943 | 3471131 | INA | Field Nation | Published | OK |  |  | 2026-04-10 | 09:00 |  | 2026-04-10 | 09:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
3351 | 3471775 | IMT | Field Nation | Published | OK |  |  | 2026-04-02 | 11:30 |  | 2026-04-02 | 11:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
3788 | 3471570 | IMT | Field Nation | Assigned | Error | Warren Katz | Warren Katz | 2026-04-02 | 08:00 |  | 2026-04-02 | 08:00 | Error | OK | OK | OK | No | No | None | Error | IE & FN Status is not OK
3850 | 3458214 | IIN | Field Nation | Assigned | Error |  | Ian Scott | 2026-04-15 | 07:00 |  | 2026-04-15 | 07:00 | Error | OK | OK | Error | No | No | None | Error | IE & FN Status is not OK; IE FE Name ≠ FN FE Name
5048 | 3439532 | IIN | Field Nation | Published | OK |  |  | 2026-04-30 | 09:30 |  | 2026-04-30 | 09:30 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
5049 | 3439533 | ITD | Field Nation | Published | OK |  |  | 2026-04-30 | 23:59 |  | 2026-04-30 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
5069 | 3446245 | IIN | Field Nation | Published | OK |  |  | 2026-04-09 | 12:00 |  | 2026-04-09 | 12:00 | OK | OK | OK | OK | No | No | None | Matched | All checks passed
5070 | 3446246 | ITD | Field Nation | Published | OK |  |  | 2026-04-09 | 23:59 |  | 2026-04-09 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception

## Errors Only
Errors Only
Core Ticket Data |  |  |  |  | Inside Edge | [5 empty] | Field Nation |  | Validation
Source Row | Acuative Ticket | Ticket Type | Assigned Company | FN Status | IE & FN Status | IE FE Name | FN FE Name | IE Due Date | IE Due Time | IE Scheduled | FN Scheduled Date | FN Scheduled Time | Status Check | Date Check | Time Check | Name Check | Date Exception Applied | Time Exception Applied | Exception Type | Final Result | Issue Details
46 | 3470793 | IIN | Field Nation | Work Done | Error | Abdul Akilo | Abdul Akilo | 2026-04-01 | 08:00 | 2026-04-01 08:00 | 2026-04-01 | 08:00 | Error | OK | OK | OK | No | No | None | Error | IE & FN Status is not OK
47 | 3470843 | ISS | Field Nation | Work Done | Error | Michael Hiter | Michael Hiter | 2026-04-01 | 08:30 | 2026-04-01 08:30 | 2026-04-01 | 08:30 | Error | OK | OK | OK | No | No | None | Error | IE & FN Status is not OK
50 | 3454713 | IIN | Field Nation | Work Done | Error | Daniel Ali | Daniel Ali | 2026-04-01 | 10:00 | 2026-04-01 10:00 | 2026-04-01 | 10:00 | Error | OK | OK | OK | No | No | None | Error | IE & FN Status is not OK
51 | 3470876 | ITR | Field Nation | Work Done | Error | William Ferguson | William Ferguson | 2026-04-01 | 10:30 | 2026-04-01 10:30 | 2026-04-01 | 09:45 | Error | OK | OK | OK | No | Yes | ITR-Time | Error | IE & FN Status is not OK; Time mismatch accepted by ITR exception
52 | 3471336 | IMO | Field Nation | Work Done | Error | Leon Cunningham | Leon Cunningham | 2026-04-01 | 11:00 | 2026-04-01 11:00 | 2026-04-01 | 11:00 | Error | OK | OK | OK | No | No | None | Error | IE & FN Status is not OK
53 | 3471337 | IMO | Field Nation | Work Done | Error | Mark Paulsen | Mark Paulsen | 2026-04-01 | 11:00 | 2026-04-01 11:00 | 2026-04-01 | 11:00 | Error | OK | OK | OK | No | No | None | Error | IE & FN Status is not OK
54 | 3471571 | IMT | Field Nation | Work Done | Error | Ashton Alva | Ashton Alva | 2026-04-01 | 11:00 | 2026-04-01 11:00 | 2026-04-01 | 11:00 | Error | OK | OK | OK | No | No | None | Error | IE & FN Status is not OK
55 | 3470877 | IIN | Field Nation | Work Done | Error | William Ferguson | William Ferguson | 2026-04-01 | 11:00 | 2026-04-01 11:00 | 2026-04-01 | 11:00 | Error | OK | OK | OK | No | No | None | Error | IE & FN Status is not OK
61 | 3470135 | ICS | Field Nation | Work Done | Error | Juan Clark | Juan Clark | 2026-04-01 | 13:00 | 2026-04-01 13:00 | 2026-04-01 | 13:00 | Error | OK | OK | OK | No | No | None | Error | IE & FN Status is not OK
112 | 3465746 | IIN | Field Nation | Assigned | OK | Gary L. Symons | Gary Symons | 2026-04-02 | 09:00 | 2026-04-02 09:00 | 2026-04-02 | 09:00 | OK | OK | OK | Error | No | No | None | Error | IE FE Name ≠ FN FE Name
130 | 3442000 | IIN | Field Nation | Assigned | OK | Ahmed O. Ali | Ahmed Ali | 2026-04-02 | 09:30 | 2026-04-02 09:30 | 2026-04-02 | 09:30 | OK | OK | OK | Error | No | No | None | Error | IE FE Name ≠ FN FE Name
231 | 3442001 | ITD | Field Nation | Assigned | OK | Ahmed O. Ali | Ahmed Ali | 2026-04-02 | 23:59 | 2026-04-02 23:59 | 2026-04-02 | 09:30 | OK | OK | OK | Error | No | Yes | ITD-Time | Error | IE FE Name ≠ FN FE Name; Time mismatch accepted by ITD exception
429 | 3471280 | INA | Field Nation | Assigned | OK | Eduardo J. Saucedo | Eduardo Saucedo | 2026-04-07 | 09:00 | 2026-04-07 09:00 | 2026-04-07 | 09:00 | OK | OK | OK | Error | No | No | None | Error | IE FE Name ≠ FN FE Name
514 | 3445944 | IIN | Field Nation | Assigned | OK | Suresh Venkatachalam | Suresh Venkatachalam | 2026-04-08 | 09:30 | 2026-04-08 09:30 | 2026-04-08 | 03:30 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
708 | 3458530 | IIN | Field Nation | Assigned | OK | Stefalonicus A. Marcius | Stephanicus Marcyus | 2026-04-13 | 05:00 | 2026-04-13 05:00 | 2026-04-13 | 05:00 | OK | OK | OK | Error | No | No | None | Error | IE FE Name ≠ FN FE Name
875 | 3437353 | IIN | Field Nation | Assigned | OK | Ndifreke Asuquo | Ndifreke Asuquo | 2026-04-15 | 12:00 | 2026-04-15 12:00 | 2026-04-15 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1182 | 3446070 | IIN | Field Nation | Assigned | OK | Todd John Soukoreff | Chris Born | 2026-04-23 | 10:30 | 2026-04-23 10:30 | 2026-04-23 | 10:30 | OK | OK | OK | Error | No | No | None | Error | IE FE Name ≠ FN FE Name
1204 | 3446071 | ITD | Field Nation | Assigned | OK | Todd John Soukoreff | Chris Born | 2026-04-23 | 23:59 | 2026-04-23 23:59 | 2026-04-23 | 08:00 | OK | OK | OK | Error | No | Yes | ITD-Time | Error | IE FE Name ≠ FN FE Name; Time mismatch accepted by ITD exception
1246 | 3468199 | IIN | Field Nation | Assigned | OK | Gary L. Symons | Gary Symons | 2026-04-27 | 09:00 | 2026-04-27 09:00 | 2026-04-27 | 09:00 | OK | OK | OK | Error | No | No | None | Error | IE FE Name ≠ FN FE Name
1284 | 3469172 | IIN | Field Nation | Assigned | OK |  | Faisal Suleman | 2026-04-28 | 07:00 | 2026-04-28 07:00 | 2026-04-28 | 07:00 | OK | OK | OK | Error | No | No | None | Error | IE FE Name ≠ FN FE Name
1285 | 3469176 | IIN | Field Nation | Assigned | OK |  | OLADAPO OLIYIDE | 2026-04-28 | 07:00 | 2026-04-28 07:00 | 2026-04-28 | 07:00 | OK | OK | OK | Error | No | No | None | Error | IE FE Name ≠ FN FE Name
1394 | 3439445 | IIN | Field Nation | Assigned | OK | Daniel L. Durham | Daniel Durham | 2026-04-30 | 13:00 | 2026-04-30 13:00 | 2026-04-30 | 13:00 | OK | OK | OK | Error | No | No | None | Error | IE FE Name ≠ FN FE Name
1410 | 3439446 | ITD | Field Nation | Assigned | OK | Daniel L. Durham | Daniel Durham | 2026-04-30 | 23:59 | 2026-04-30 23:59 | 2026-04-30 | 15:00 | OK | OK | OK | Error | No | Yes | ITD-Time | Error | IE FE Name ≠ FN FE Name; Time mismatch accepted by ITD exception
1455 | 3471435 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-05-04 | 23:59 | 2026-05-04 10:00 | 2026-05-04 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1491 | 3471436 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-05-05 | 23:59 | 2026-05-05 10:00 | 2026-05-05 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1522 | 3471438 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-05-06 | 23:59 | 2026-05-06 10:00 | 2026-05-06 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1541 | 3471439 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-05-07 | 23:59 | 2026-05-07 10:00 | 2026-05-07 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1568 | 3470903 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-08 | 23:59 | 2026-06-08 10:00 | 2026-06-08 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1569 | 3470904 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-09 | 23:59 | 2026-06-09 10:00 | 2026-06-09 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1571 | 3470905 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-10 | 23:59 | 2026-06-10 10:00 | 2026-06-10 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1574 | 3470906 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-11 | 23:59 | 2026-06-11 10:00 | 2026-06-11 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1577 | 3470908 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-12 | 23:59 | 2026-06-12 10:00 | 2026-06-12 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1580 | 3470909 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-13 | 23:59 | 2026-06-13 10:00 | 2026-06-13 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1583 | 3470910 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-14 | 23:59 | 2026-06-14 10:00 | 2026-06-14 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1586 | 3470911 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-15 | 23:59 | 2026-06-15 10:00 | 2026-06-15 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1589 | 3470912 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-16 | 23:59 | 2026-06-16 10:00 | 2026-06-16 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1592 | 3470913 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-17 | 23:59 | 2026-06-17 10:00 | 2026-06-17 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1596 | 3470914 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-18 | 23:59 | 2026-06-18 10:00 | 2026-06-18 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1599 | 3470915 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-19 | 23:59 | 2026-06-19 10:00 | 2026-06-19 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1602 | 3470916 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-20 | 23:59 | 2026-06-20 10:00 | 2026-06-20 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1605 | 3470917 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-21 | 23:59 | 2026-06-21 10:00 | 2026-06-21 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1608 | 3470919 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-22 | 23:59 | 2026-06-22 10:00 | 2026-06-22 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1609 | 3470922 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-23 | 23:59 | 2026-06-23 10:00 | 2026-06-23 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1610 | 3470923 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-24 | 23:59 | 2026-06-24 10:00 | 2026-06-24 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1611 | 3470924 | IIN | Field Nation | Assigned | OK | Michael Pavelchik | Michael Pavelchik | 2026-06-25 | 23:59 | 2026-06-25 10:00 | 2026-06-25 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
1612 | 3419497 | IIN | Field Nation | Assigned | OK | Adeola Ajayi | Adeola Ajayi | 2026-08-19 | 12:00 | 2026-08-19 12:00 | 2026-08-19 | 08:00 | OK | OK | Error | OK | No | No | None | Error | Due Time ≠ FN Scheduled Time
3788 | 3471570 | IMT | Field Nation | Assigned | Error | Warren Katz | Warren Katz | 2026-04-02 | 08:00 |  | 2026-04-02 | 08:00 | Error | OK | OK | OK | No | No | None | Error | IE & FN Status is not OK
3850 | 3458214 | IIN | Field Nation | Assigned | Error |  | Ian Scott | 2026-04-15 | 07:00 |  | 2026-04-15 | 07:00 | Error | OK | OK | Error | No | No | None | Error | IE & FN Status is not OK; IE FE Name ≠ FN FE Name

## Exceptions
Exceptions
Core Ticket Data |  |  |  |  | Inside Edge | [5 empty] | Field Nation |  | Validation
Source Row | Acuative Ticket | Ticket Type | Assigned Company | FN Status | IE & FN Status | IE FE Name | FN FE Name | IE Due Date | IE Due Time | IE Scheduled | FN Scheduled Date | FN Scheduled Time | Status Check | Date Check | Time Check | Name Check | Date Exception Applied | Time Exception Applied | Exception Type | Final Result | Issue Details
51 | 3470876 | ITR | Field Nation | Work Done | Error | William Ferguson | William Ferguson | 2026-04-01 | 10:30 | 2026-04-01 10:30 | 2026-04-01 | 09:45 | Error | OK | OK | OK | No | Yes | ITR-Time | Error | IE & FN Status is not OK; Time mismatch accepted by ITR exception
71 | 3441779 | ITD | Field Nation | Assigned | OK | Ozni Benson | Ozni Benson | 2026-04-01 | 23:59 | 2026-04-01 20:00 | 2026-04-01 | 11:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
84 | 3441041 | ITD | Field Nation | Assigned | OK | Chris Esswein | Chris Esswein | 2026-04-01 | 23:59 | 2026-04-01 23:59 | 2026-04-01 | 14:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
209 | 3445979 | ITD | Field Nation | Assigned | OK | Harb Salman | Harb Salman | 2026-04-02 | 23:59 | 2026-04-02 15:00 | 2026-04-02 | 13:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
222 | 3440665 | ITD | Field Nation | Assigned | OK | Olivia Wilcroft | Olivia Wilcroft | 2026-04-02 | 23:59 | 2026-04-02 23:00 | 2026-04-02 | 10:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
230 | 3439437 | ITD | Field Nation | Assigned | OK | Ricky Christopher | Ricky Christopher | 2026-04-02 | 23:59 | 2026-04-02 23:59 | 2026-04-02 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
231 | 3442001 | ITD | Field Nation | Assigned | OK | Ahmed O. Ali | Ahmed Ali | 2026-04-02 | 23:59 | 2026-04-02 23:59 | 2026-04-02 | 09:30 | OK | OK | OK | Error | No | Yes | ITD-Time | Error | IE FE Name ≠ FN FE Name; Time mismatch accepted by ITD exception
232 | 3446262 | ITD | Field Nation | Assigned | OK | Ameh Atokolo | Ameh Atokolo | 2026-04-02 | 23:59 | 2026-04-02 23:59 | 2026-04-02 | 11:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
233 | 3446061 | ITD | Field Nation | Assigned | OK | David Ogunwobi | David Ogunwobi | 2026-04-02 | 23:59 | 2026-04-02 23:59 | 2026-04-02 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
234 | 3446085 | ITD | Field Nation | Assigned | OK | Yvan Dimitri Dzuakou Todem | Yvan Dimitri DZUAKOU TODEM | 2026-04-02 | 23:59 | 2026-04-02 23:59 | 2026-04-02 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
309 | 3439976 | ITD | Field Nation | Assigned | OK | Jason Wagster | Jason Wagster | 2026-04-03 | 23:59 | 2026-04-03 23:59 | 2026-04-03 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
310 | 3446083 | ITD | Field Nation | Assigned | OK | Neuer Alsibai | Neuer Alsibai | 2026-04-03 | 23:59 | 2026-04-03 23:59 | 2026-04-03 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
402 | 3446015 | ITD | Field Nation | Assigned | OK | Sai Prakash Reddy Atluri | Sai Prakash Reddy Atluri | 2026-04-06 | 23:59 | 2026-04-06 20:00 | 2026-04-06 | 10:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
479 | 3440965 | ITD | Field Nation | Assigned | OK | Amin Sanchez | Amin Sanchez | 2026-04-07 | 23:59 | 2026-04-07 20:00 | 2026-04-07 | 11:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
481 | 3439928 | ITD | Field Nation | Assigned | OK | Harpreet Singh | Harpreet Singh | 2026-04-07 | 23:59 | 2026-04-07 23:59 | 2026-04-07 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
482 | 3445963 | ITD | Field Nation | Assigned | OK | Kabir Kareem | KABIR KAREEM | 2026-04-07 | 23:59 | 2026-04-07 23:59 | 2026-04-07 | 06:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
483 | 3446031 | ITD | Field Nation | Assigned | OK | Adewale Adesona | Adewale Adesona | 2026-04-07 | 23:59 | 2026-04-07 23:59 | 2026-04-07 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
556 | 3441495 | ITD | Field Nation | Assigned | OK | Daniel Ali | Daniel Ali | 2026-04-08 | 23:59 | 2026-04-08 20:00 | 2026-04-08 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
557 | 3441537 | ITD | Field Nation | Assigned | OK | Ricki Cole | Ricki Cole | 2026-04-08 | 23:59 | 2026-04-08 20:00 | 2026-04-08 | 10:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
558 | 3440084 | ITD | Field Nation | Assigned | OK | Jerome Chambers | Jerome Chambers | 2026-04-08 | 23:59 | 2026-04-08 20:00 | 2026-04-08 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
562 | 3445945 | ITD | Field Nation | Assigned | OK | Suresh Venkatachalam | Suresh Venkatachalam | 2026-04-08 | 23:59 | 2026-04-08 23:59 | 2026-04-08 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
563 | 3445985 | ITD | Field Nation | Assigned | OK | Oladapo Oliyide | OLADAPO OLIYIDE | 2026-04-08 | 23:59 | 2026-04-08 23:59 | 2026-04-08 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
564 | 3446067 | ITD | Field Nation | Assigned | OK | Nnamdi Igbokwe | Nnamdi Igbokwe | 2026-04-08 | 23:59 | 2026-04-08 23:59 | 2026-04-08 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
632 | 3441435 | ITD | Field Nation | Assigned | OK | Tom Perachio | Tom Perachio | 2026-04-09 | 23:59 | 2026-04-09 20:00 | 2026-04-09 | 11:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
633 | 3440060 | ITD | Field Nation | Assigned | OK | Jonathan Taufer | Jonathan Taufer | 2026-04-09 | 23:59 | 2026-04-09 20:00 | 2026-04-09 | 12:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
639 | 3441307 | ITD | Field Nation | Assigned | OK | Jason Wagster | Jason Wagster | 2026-04-09 | 23:59 | 2026-04-09 23:59 | 2026-04-09 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
643 | 3446027 | ITD | Field Nation | Assigned | OK | Gagandeep Singh | Gagandeep Singh | 2026-04-10 | 23:59 | 2026-04-10 08:00 | 2026-04-10 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
694 | 3441457 | ITD | Field Nation | Assigned | OK | Lydell Emerson | Lydell Emerson | 2026-04-10 | 23:59 | 2026-04-10 23:59 | 2026-04-10 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
695 | 3440192 | ITD | Field Nation | Assigned | OK | Johnnie Mcleod | Johnnie McLeod | 2026-04-10 | 23:59 | 2026-04-10 23:59 | 2026-04-10 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
696 | 3445975 | ITD | Field Nation | Assigned | OK | Kail Vigneswaran | Kail Vigneswaran | 2026-04-10 | 23:59 | 2026-04-10 23:59 | 2026-04-10 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
765 | 3441103 | ITD | Field Nation | Assigned | OK | Ademola Kuku | Ademola Kuku | 2026-04-13 | 23:59 | 2026-04-13 20:00 | 2026-04-13 | 11:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
768 | 3446029 | ITD | Field Nation | Assigned | OK | Oladapo Oliyide | OLADAPO OLIYIDE | 2026-04-13 | 23:59 | 2026-04-13 23:59 | 2026-04-13 | 13:45 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
836 | 3441147 | ITD | Field Nation | Assigned | OK | Joshua Evans | Joshua Evans | 2026-04-14 | 23:59 | 2026-04-14 23:59 | 2026-04-14 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
837 | 3441151 | ITD | Field Nation | Assigned | OK | Mario Boatwright | Mario Boatwright | 2026-04-14 | 23:59 | 2026-04-14 23:59 | 2026-04-14 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
838 | 3440213 | ITD | Field Nation | Assigned | OK | Daniel Jordan | Daniel Jordan | 2026-04-14 | 23:59 | 2026-04-14 23:59 | 2026-04-14 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
839 | 3445999 | ITD | Field Nation | Assigned | OK | Dawit Telahun | Dawit Telahun | 2026-04-14 | 23:59 | 2026-04-14 23:59 | 2026-04-14 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
899 | 3441377 | ITD | Field Nation | Assigned | OK | Frank Shoffner | FRANK SHOFFNER | 2026-04-15 | 23:59 | 2026-04-15 23:59 | 2026-04-15 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
900 | 3446001 | ITD | Field Nation | Assigned | OK | David Edojah | David Edojah | 2026-04-15 | 23:59 | 2026-04-15 23:59 | 2026-04-15 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
901 | 3446091 | ITD | Field Nation | Assigned | OK | Abdurzag Abdunur | Abdurzag Abdunur | 2026-04-15 | 23:59 | 2026-04-15 23:59 | 2026-04-15 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
959 | 3441057 | ITD | Field Nation | Assigned | OK | Overton Kelly | Overton Kelly | 2026-04-16 | 23:59 | 2026-04-16 23:00 | 2026-04-16 | 11:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
965 | 3441079 | ITD | Field Nation | Assigned | OK | Dwiuan White | Dwiuan White | 2026-04-16 | 23:59 | 2026-04-16 23:59 | 2026-04-16 | 12:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
966 | 3445967 | ITD | Field Nation | Assigned | OK | Gull Hassan | Gull Hassan | 2026-04-16 | 23:59 | 2026-04-16 23:59 | 2026-04-16 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
967 | 3446035 | ITD | Field Nation | Assigned | OK | Gagandeep Singh | Gagandeep Singh | 2026-04-16 | 23:59 | 2026-04-16 23:59 | 2026-04-16 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1002 | 3439464 | ITD | Field Nation | Assigned | OK | Jamiel Shelton | Jamiel Shelton | 2026-04-17 | 23:59 | 2026-04-17 17:00 | 2026-04-17 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1003 | 3441199 | ITD | Field Nation | Assigned | OK | Stephen Antwi | Stephen Antwi | 2026-04-17 | 23:59 | 2026-04-17 23:59 | 2026-04-17 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1004 | 3441201 | ITD | Field Nation | Assigned | OK | Jamiel Shelton | Jamiel Shelton | 2026-04-17 | 23:59 | 2026-04-17 23:59 | 2026-04-17 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1005 | 3446268 | ITD | Field Nation | Assigned | OK | Josh Daynes | Josh Daynes | 2026-04-17 | 23:59 | 2026-04-17 23:59 | 2026-04-17 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1049 | 3441731 | ITD | Field Nation | Assigned | OK | Derek Francis Domingo | Derek Francis Domingo | 2026-04-20 | 23:59 | 2026-04-20 17:00 | 2026-04-20 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1051 | 3446224 | ITD | Field Nation | Assigned | OK | Kabir Kareem | KABIR KAREEM | 2026-04-20 | 23:59 | 2026-04-20 23:59 | 2026-04-20 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1052 | 3445971 | ITD | Field Nation | Assigned | OK | Victor Isac | Victor Isac | 2026-04-20 | 23:59 | 2026-04-20 23:59 | 2026-04-20 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1103 | 3441333 | ITD | Field Nation | Assigned | OK | Daniel Jordan | Daniel Jordan | 2026-04-21 | 23:59 | 2026-04-21 23:59 | 2026-04-21 | 03:15 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1104 | 3441663 | ITD | Field Nation | Assigned | OK | Mor Ndiaye | Mor Ndiaye | 2026-04-21 | 23:59 | 2026-04-21 23:59 | 2026-04-21 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1105 | 3445973 | ITD | Field Nation | Assigned | OK | Oladapo Oliyide | OLADAPO OLIYIDE | 2026-04-21 | 23:59 | 2026-04-21 23:59 | 2026-04-21 | 12:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1106 | 3446003 | ITD | Field Nation | Assigned | OK | Kabir Kareem | KABIR KAREEM | 2026-04-21 | 23:59 | 2026-04-21 23:59 | 2026-04-21 | 12:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1107 | 3446112 | ITD | Field Nation | Assigned | OK | Chris Born | Chris Born | 2026-04-21 | 23:59 | 2026-04-21 23:59 | 2026-04-21 | 12:45 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1158 | 3445991 | ITD | Field Nation | Assigned | OK | Kabir Kareem | KABIR KAREEM | 2026-04-22 | 23:59 | 2026-04-22 23:59 | 2026-04-22 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1159 | 3446105 | ITD | Field Nation | Assigned | OK | Oladapo Oliyide | OLADAPO OLIYIDE | 2026-04-22 | 23:59 | 2026-04-22 23:59 | 2026-04-22 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1197 | 3439617 | ITD | Field Nation | Assigned | OK | Erin Scofield | Erin Scofield | 2026-04-23 | 23:59 | 2026-04-23 20:00 | 2026-04-23 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1201 | 3446226 | ITD | Field Nation | Assigned | OK | Oladapo Oliyide | OLADAPO OLIYIDE | 2026-04-23 | 23:59 | 2026-04-23 23:59 | 2026-04-23 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1202 | 3445995 | ITD | Field Nation | Assigned | OK | Dawit Telahun | Dawit Telahun | 2026-04-23 | 23:59 | 2026-04-23 23:59 | 2026-04-23 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1203 | 3445997 | ITD | Field Nation | Assigned | OK | Shumail Feroz | Shumail Feroz | 2026-04-23 | 23:59 | 2026-04-23 23:59 | 2026-04-23 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1204 | 3446071 | ITD | Field Nation | Assigned | OK | Todd John Soukoreff | Chris Born | 2026-04-23 | 23:59 | 2026-04-23 23:59 | 2026-04-23 | 08:00 | OK | OK | OK | Error | No | Yes | ITD-Time | Error | IE FE Name ≠ FN FE Name; Time mismatch accepted by ITD exception
1242 | 3446228 | ITD | Field Nation | Assigned | OK | Kabir Kareem | KABIR KAREEM | 2026-04-24 | 23:59 | 2026-04-24 23:59 | 2026-04-24 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1243 | 3446079 | ITD | Field Nation | Assigned | OK | Renat Galiev | Renat Galiev | 2026-04-24 | 23:59 | 2026-04-24 23:59 | 2026-04-24 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1280 | 3441447 | ITD | Field Nation | Assigned | OK | Ashley Mattera | Ashley Mattera | 2026-04-27 | 23:59 | 2026-04-27 23:59 | 2026-04-27 | 09:30 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1281 | 3439611 | ITD | Field Nation | Assigned | OK | Joshua Evans | Joshua Evans | 2026-04-27 | 23:59 | 2026-04-27 23:59 | 2026-04-27 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1282 | 3445965 | ITD | Field Nation | Assigned | OK | Kabir Kareem | KABIR KAREEM | 2026-04-27 | 23:59 | 2026-04-27 23:59 | 2026-04-27 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1326 | 3446238 | ITD | Field Nation | Assigned | OK | Asad Khalid Ansari | Asad Khalid Ansari | 2026-04-28 | 23:59 | 2026-04-28 23:59 | 2026-04-28 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1371 | 3441511 | ITD | Field Nation | Assigned | OK | Ned Gill | Ned Gill | 2026-04-29 | 23:59 | 2026-04-29 20:00 | 2026-04-29 | 11:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1410 | 3439446 | ITD | Field Nation | Assigned | OK | Daniel L. Durham | Daniel Durham | 2026-04-30 | 23:59 | 2026-04-30 23:59 | 2026-04-30 | 15:00 | OK | OK | OK | Error | No | Yes | ITD-Time | Error | IE FE Name ≠ FN FE Name; Time mismatch accepted by ITD exception
1411 | 3440531 | ITD | Field Nation | Assigned | OK | Oladipupo Ogungbile | Oladipupo Ogungbile | 2026-04-30 | 23:59 | 2026-04-30 23:59 | 2026-04-30 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1412 | 3446009 | ITD | Field Nation | Assigned | OK | Rupinderjit Singh Malhi | Rupinderjit Singh Malhi | 2026-04-30 | 23:59 | 2026-04-30 23:59 | 2026-04-30 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1445 | 3441005 | ITD | Field Nation | Assigned | OK | Anthony Clark | Anthony Clark | 2026-05-01 | 23:59 | 2026-05-01 17:00 | 2026-05-01 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1447 | 3446021 | ITD | Field Nation | Assigned | OK | Richard Dey | Richard Dey | 2026-05-01 | 23:59 | 2026-05-01 23:59 | 2026-05-01 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1448 | 3446254 | ITD | Field Nation | Assigned | OK | Chris Born | Chris Born | 2026-05-01 | 23:59 | 2026-05-01 23:59 | 2026-05-01 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1533 | 3440078 | ITD | Field Nation | Assigned | OK | Zachary Jones | Zachary Jones | 2026-05-06 | 23:59 | 2026-05-06 23:59 | 2026-05-06 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
1534 | 3440237 | ITD | Field Nation | Assigned | OK | Brian Kloss | Brian Kloss | 2026-05-06 | 23:59 | 2026-05-06 23:59 | 2026-05-06 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
5049 | 3439533 | ITD | Field Nation | Published | OK |  |  | 2026-04-30 | 23:59 |  | 2026-04-30 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception
5070 | 3446246 | ITD | Field Nation | Published | OK |  |  | 2026-04-09 | 23:59 |  | 2026-04-09 | 08:00 | OK | OK | OK | OK | No | Yes | ITD-Time | Matched | Time mismatch accepted by ITD exception

## Rules
Applied Validation Rules
Rule | Description
Validation Scope | Only rows where Assigned Company = Field Nation are treated as comparable rows.
Status Rule | IE & FN Status must equal OK.
Date Rule | IE Due Date must match FN Scheduled Date.
Date Exception | If the dates differ, the row is still valid only when Ticket Type = ITD.
Time Rule | IE Due Time must match FN Scheduled Time.
Time Exception | If the time differs, the row is still valid when Ticket Type = ITD or ITR.
Name Rule | IE Assigned FE Name must match FN FE Name after trimming and case normalization.
Final Result | A row is Matched only when status, date, time, and name checks are valid after applying the above exceptions.
Row Colors | Green = matched, Red = error, Yellow = matched through an exception.